## Sheet1
SrNo | SrNo | SrNo | Role | Task | Sub Task | API Name | Hours | Developer Name
1 |  |  | All
| 1 |  |  | Authentication
|  | 1 |  |  | Login | User Login | 4 | Vaishnavi Tekade
|  | 2 |  |  | Change Password | Change password | 4 | sakshi shewale
|  | 3 |  |  | Forget Password | Verify email | 4 | Vaishnavi Tekade
[6 empty] | Forget password | 4 | Vaishnavi Tekade
| 2 |  |  | RBAC
|  | 1 |  |  | User Details | Insert user | 4 | sakshi shewale
[6 empty] | Delete user | 4 | sakshi shewale
[6 empty] | Get user data | 4 | sakshi shewale
[6 empty] | Edit user | 4 | sakshi shewale
[6 empty] | Get user list | 4 | sakshi shewale
[6 empty] | Filter user (and also provide the API for dropdowns if needed). | 4 | sakshi shewale
|  | 2 |  |  | Role Details | Insert role | 4 | sakshi shewale
[6 empty] | Delete role | 4 | sakshi shewale
[6 empty] | Get role data | 4 | sakshi shewale
[6 empty] | Edit role | 4 | sakshi shewale
[6 empty] | Get role list | 4 | sakshi shewale
[6 empty] | Filter user (and also provide the API for dropdowns if needed). | 4 | sakshi shewale
|  | 3 |  |  | Assign Role | User dropdown api | 4 | Vaishnavi Tekade
[6 empty] | Role dropdown api | 4 | Vaishnavi Tekade
[6 empty] | Inset assign role | 4 | Vaishnavi Tekade
[6 empty] | Delete assign role | 4 | Vaishnavi Tekade
[6 empty] | Get assign role data | 4 | Vaishnavi Tekade
[6 empty] | Edit assign role | 4 | Vaishnavi Tekade
[6 empty] | Get assign list | 4 | Vaishnavi Tekade
[6 empty] | Filter user (and also provide the API for dropdowns if needed). | 4 | Vaishnavi Tekade
|  | 4 |  |  | Assign Rights | Bind role | 4 | Vaishnavi Tekade
[6 empty] | Bind menu | 4 | Vaishnavi Tekade
[6 empty] | Bind sub menu | 4 | Vaishnavi Tekade
[6 empty] | Insert assign rights | 4 | Vaishnavi Tekade
[6 empty] | Delete assign rights | 4 | Vaishnavi Tekade
[6 empty] | Get assign rights list | 4 | Vaishnavi Tekade
[6 empty] | Filter user (and also provide the API for dropdowns if needed). | 4 | Vaishnavi Tekade
2 |  |  | Admin
| 1 |  |  | Dashboard
|  | 1 |  |  | Show Leave | (ask what to show on dashboard )
| 2 |  |  | Configuration
|  | 1 |  |  | Company | Insert company | 4 | sakshi shewale
[6 empty] | View company list | 4 | sakshi shewale
[6 empty] | View company data | 4 | sakshi shewale
[6 empty] | Edit company | 4 | sakshi shewale
[6 empty] | Delete company | 4 | sakshi shewale
[6 empty] | Filter user (and also provide the API for dropdowns if needed). | 4 | sakshi shewale
| 3 |  |  | Salary | get data to generate salary slip ( generateSalarySlipData) | Need Discussion
| 4 |  |  | Leave Management
|  | 1 |  |  | Show all leaves | get all leaves | 4 | sakshi shewale
3 |  |  | HR
| 1 |  |  | Dashboard
|  | 1 |  |  | Show all accepted leaves to HR | (ask what to show on dashboard )
| 2 |  |  | Salary | get data to generate salary slip ( generateSalarySlipData) | Need Discussion
| 3 |  |  | Leave Management
|  | 1 |  |  | Show all accepted leaves to HR | getManagerApprovedLeaves | 4 | Vaishnavi Tekade
|  | 2 |  |  | Approve leave (HR) | approveLeaveHR | 4 | Vaishnavi Tekade
|  | 3 |  |  | Send email | sendLeaveEmail | 4 | Vaishnavi Tekade
4 |  |  | Reporting Manager
| 1 |  |  | Dashboard
[5 empty] | Show all leaves | (ask what to show on dashboard )
| 2 |  |  | Leave Management
|  | 1 |  |  | Show all leaves to reporting manager | getLeavesForManager | 4 | sakshi shewale
|  | 2 |  |  | Approve leave (Manager) | approveLeave | 4 | sakshi shewale
5 |  |  | Database & UD for HRMS
|  |  |  | Design database schema |  |  | 4 | sakshi shewale
|  |  |  | Create architecture In Asp.Net |  |  | 8 | Vaishnavi Tekade
|  |  |  | Create table structure |  |  | 8 | sakshi shewale
Need Salary slip structure